{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["研发计划","资源依赖"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"研发计划","index":0,"n_rows":61,"n_cols":10,"rows_kept":61,"cut":false,"hidden":false,"merged":[[5,2,5,3],[3,0,15,0],[16,0,40,0],[41,0,60,0],[3,1,5,1],[6,1,15,1],[16,1,27,1],[28,1,38,1],[41,1,59,1],[3,2,4,2],[6,2,7,2],[8,2,11,2],[12,2,15,2],[16,2,17,2],[18,2,20,2],[21,2,25,2],[26,2,27,2],[30,2,31,2],[32,2,36,2],[37,2,38,2],[41,2,42,2],[43,2,46,2],[47,2,49,2],[50,2,52,2],[53,2,54,2],[55,2,59,2],[0,0,1,9]]}
["任务"]
[]
[null,"任务","子任务","子任务","资源","状态","开始","结束","贡献度（工时）","说明"]
["系统设计","需求设计","企微端设计","（UI设计）","陈小燕","已完成","2022-03-17","2022-03-24",7]
[null,null,null,"评审","曹刚","已完成","2022-03-17","2022-03-24",2,"对设计进行评审，提出修改意见"]
[null,null,"管理后台设计",null,"陈小燕","未开始",null,null,null,"待定"]
[null,"系统设计","数据库设计","数据库设计","马泽伟","已完成","2022-03-14","2022-03-24",3]
[null,null,null,"评审","曹  刚","已完成","2022-03-14","2022-03-24",1]
[null,null,"学院系统集成","sso集成接口",null,"未开始"]
[null,null,null,"组织架构数据接口",null,"未开始"]
[null,null,null,"教学数据接口",null,"未开始"]
[null,null,null,"学生信息接口",null,"未开始"]
[null,null,"系统架构","数据同步方案","曹  刚","已完成",null,null,1]
[null,null,null,"应用技术架构设计","曹  刚","未开始",null,null,1]
[null,null,null,"应用部署架构设计","曹  刚","未开始",null,null,1]
[null,null,null,"应用数据架构设计","曹  刚","已完成",null,null,1]
["企微学生端","页面开发","开发框架","uniapp开发框架","欧楚伦","已完成","2022-03-14","2022-03-24",3]
[null,null,null,"企微登录集成","欧楚伦","未开始","2022-04-15","2022-04-18",null,"企业微信集成"]
[null,null,"首页","banner","欧楚伦","未开始","2022-03-28","2022-03-28",0.5]
[null,null,null,"日程安排","欧楚伦","未开始","2022-03-28","2022-03-29",0.5]
[null,null,null,"专业分流","欧楚伦","未开始","2022-03-29","2022-03-29",0.5]
[null,null,"专业分流","分流名额","欧楚伦","未开始","2022-03-30","2022-03-31",2]
[null,null,null,"本人成绩","欧楚伦","未开始","2022-04-01","2022-04-01",1]
[null,null,null,"特别申请","欧楚伦","未开始","2022-04-02","2022-04-07",3]
[null,null,null,"专业分流","欧楚伦","未开始","2022-04-08","2022-04-11",2]
[null,null,null,"进度查询","欧楚伦","未开始","2022-04-12","2022-04-12",1]
[null,null,"我的","我的首页","欧楚伦","未开始","2022-04-13","2022-04-13",1]
[null,null,null,"个人资料编辑","欧楚伦","未开始","2022-04-14","2022-04-14",1]
[null,"API开发","开发框架",null,"曹  刚","已完成","2022-03-14","2022-03-24",2]
[null,null,"企微登录集成",null,"曹  刚","未开始",null,null,null,"1、教务系统同步学生信息至“专业分流系统”\n2、学生点击企微入口“专业分流系统”，系统获取学生学号等信息\n3、根据学生标识信息在系统内进行查询，判断是否存在权限\n4、登录验证成功之后返回token\n5、失败时提示无权限"]
[null,null,"首页","banner","曹  刚","进行中"]
[null,null,null,"日程安排","曹  刚","已完成"]
[null,null,"专业分流","分流名额","曹  刚","已完成"]
[null,null,null,"本人成绩","曹  刚","已完成"]
[null,null,null,"特别申请","曹  刚","未开始"]
[null,null,null,"专业分流","曹  刚","未开始"]
[null,null,null,"进度查询","曹  刚","未开始"]
[null,null,"我的","我的首页","曹  刚","未开始"]
[null,null,null,"个人资料编辑","曹  刚","未开始"]
[null,"联调",null,null,"曹  刚\n欧楚伦","未开始","2022-04-19","2022-04-21",null,"接口联调"]
[null,"测试",null,null,"欧楚伦","未开始","2022-04-22","2022-04-27",null,"功能测试"]
["管理后台","页面开发","框架","登录","马泽伟","已完成","2022-03-14","2022-03-24",4,"1、开发框架\n2、开发框架培训"]
[null,null,null,"首页","马泽伟","已完成","2022-03-14","2022-03-24",1]
[null,null,"参数设置","学生信息",null,"未开始",null,null,null,"1、学生信息列表\n2、学生信息导入（同步功能，调佣API将数据同步至分流系统）"]
[null,null,null,"日程安排","马泽伟","已完成",null,null,null,"1、日程安排数据列表（增删改查）\n2、学生信息导入（同步功能，调佣API将数据同步至分流系统）"]
[null,null,null,"特殊申请告知设置","马泽伟","已完成",null,null,null,"系统配置类别的富文本（按照学院、年份维度进行区分）"]
[null,null,null,"专业分流告知设置","马泽伟","已完成",null,null,null,"系统配置类别的富文本（按照学院、年份维度进行区分）"]
[null,null,"特别申请审批","特别申请名单","梁俊星","已完成","2022-03-30","2022-03-30",7,"特别申请数据查询"]
[null,null,null,"申请材料下载","梁俊星","已完成",null,null,null,"特别申请数据word文档格式生成"]
[null,null,null,"申请处理","梁俊星","已完成",null,null,null,"状态数据变更"]
[null,null,"专业分流数据分析","学生志愿填报报表（含导出）","梁俊星","已完成","2022-03-29","2022-03-29",7]
[null,null,null,"学生志愿填报汇总","梁俊星","已完成"]
[null,null,null,"调剂分配","马泽伟","已完成"]
[null,null,"分流结果","分流结果查看","马泽伟","进行中"]
[null,null,null,"分流结果打印","马泽伟","进行中",null,null,null,"导出excel、导出word"]
[null,null,"系统管理","组织机构管理","马泽伟","进行中"]
[null,null,null,"账号管理","马泽伟","已完成","2022-03-14","2022-03-24",1]
[null,null,null,"角色管理","马泽伟","已完成","2022-03-14","2022-03-24",1]
[null,null,null,"授权管理","马泽伟","已完成","2022-03-14","2022-03-24",1]
[]
[null,"测试",null,null,"马泽伟\n梁俊星","未开始"]

{"sheet":"资源依赖","index":1,"n_rows":7,"n_cols":2,"rows_kept":7,"cut":false,"hidden":false,"merged":[]}
["序号","说明"]
[1,"开发环境"]
[2,"企微环境"]
[3,"sso说明文档"]
[4,"组织机构、账号、权限集成说明文档"]
[5,"部署服务器资料"]
[6,"vpn环境（学院服务器需要vpn连接）"]