{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":26,"n_cols":9,"rows_kept":26,"cut":false,"hidden":false,"merged":[[7,0,11,0],[7,7,11,7],[12,3,13,3],[12,0,14,0],[7,1,13,1],[14,1,18,1],[7,2,11,2],[15,0,24,0],[7,8,11,8],[12,8,14,8],[19,1,20,1],[23,1,24,1],[12,7,14,7],[15,2,16,2],[17,2,18,2],[21,1,22,1],[21,2,22,2],[23,2,24,2],[19,2,20,2]]}
["学校",null,null,null,"W1项目设计"]
["实训时间",null,null,null,"W2项目开始"]
["上课时间",null,null,null,"W3-W5代码开发"]
["学生分组",null,"1~4人/团队(1PM、1TL、4组员)",null,"W6 项目验收"]
["讲师",null,"2人"]
[]
["项目阶段",null,"时间","环节活动","主要工作以及关键细节","参与者","主导角色","交付物","准备的文档"]
["立项-实训启动","W1","class 1","启动","1、企业、师资介绍\n2、实训总体安排介绍","全体成员",null,"1）会议记录\n2）需求规格说明书","1.文档\n  1）实训流程计划excel\n  2）实训项目excel\n  3）分组excel\n2.模板\n  1）会议记录模板\n  2）需求规格说明书模板"]
[null,null,null,"分组、角色","1、分组\n    1）分组：公布分组名单\n    2）角色介绍（PM/SA/TL/TE/SE)：\n  每个角色做什么(提供架构图的文档）\n2、定角色\n     讨论各个角色，是否需要调整角色（合理性），最后给老师反馈 ","全体成员"]
[null,null,null,"分发需求、讲解","1、分发需求，讨论需求问题\n2、用例分析","全体成员"]
[null,null,null,"团队认识","队名/口号/Logo/展示演讲solo","全体成员"]
[null,null,null,"Kick Off &. Requirement Meeting","1、由PM组织\n   1）讨论需求\n   2）出一份用户需求说明书\n   3）有会议记录","项目组"]
["架构与系统设计",null,"class 2","架构与系统设计","1.需求拆解\n    1）讨论需求问题\n2.原型设计\n    1）设计系统原型\n    2)   绘制UI","项目组",null,"1）会议记录\n2）需求规格说明书\n3）需求原型雏型出现(核心业务功能)","1.模板\n   1）会议记录模板\n   2）需求规格说明书模板\n2.原型设计网址\nhttps://www.xiaopiu.com"]
[null,null,"class 3",null,"1.原型设计\n    1）设计系统原型\n    2)   绘制UI\n2.数据库设计","项目组"]
[null,"W2","class 4","设计评审","1）需求\n2）原型\n要求：需求原型雏型出现(核心业务功能)","全体成员"]
["详细设计与编码\n集成测试与联调",null,"class 5","前端/后端授课","1.前端项目搭建\n2.后端项目搭建\n3.微信小程序项目搭建","全体成员",null,null,"1、springboot、MySQL、redis、MyBatisPlus\n2、Vue2 、element-ui\n3、uniapp"]
[null,null,null,"任务安排","1.搭建项目","项目组"]
[null,null,"class 6","前端/后端授课","1.前后端接口联调\n2.解决跨域问题","全体成员",null,null,"axios"]
[null,null,null,"任务安排","1.根据需求，按计划完成主体功能","项目组"]
[null,"W3","class 7 ~ class 9","课程安排","1.指导并解答学生问题","项目组"]
[null,null,null,"任务安排","1.根据需求，按计划完成系统功能","项目组"]
[null,"W4","class 9 ~ class 12","课程安排","1.中期阶段性演示\n2.指导并解答学生问题","全体成员"]
[null,null,null,"任务安排","1.根据需求，按计划完成系统功能","项目组"]
[null,"W5","class 13 ~ class 15","课程安排","1.指导并解答学生问题\n2.操作手册介绍","项目组"]
[null,null,null,"任务安排","1.根据需求，按计划完成系统功能\n2.编写操作手册","项目组"]
["项目验收","W6","class 16 ~ class 18","项目验收","一、项目汇报展示流程及须知：\n1、汇报小组顺序（抽签）\n2、必须提供PPT，介绍内容包含如下（但不限于）\n1）项目组基本情况\n2）项目需求介绍\n3）项目完成情况（演示）\n4）总结与展望\n3、时间要求：\n1）每组8-10分钟\n（低于8分钟、超出10分钟都要扣分，每分钟扣1分）\n2）问答互动（0-5分钟）\n4、项目演示评价标准（满分40分）\n1）演示整体印象分（占10分）\n2）系统功能演示分（20分）\n3）时间把控（5分）\n4）亮点（5分）","全体成员",null,"序号小组名（目录）\n 需求文档（目录）\n  -软件需求规格说明书.doc(required)\n  -测试用例.doc\n  -ui设计.zip\n 设计文档（目录）\n  -系统概要设计说明书.doc(required)\n 项目启动（目录）\n  -会议记录-mmDD.doc(required)\n  -组员信息表(required)\n 项目总结（目录）\n  -presentationPPT(required)\n  -贡献评价表(required)\n\n 源代码（目录）\n  -projectXXX.zip（以.zip或者.rar打包的方式）(required)\n  -readme.md(介绍用什么开发集成工具导入)(required)\n 项目发布（目录）(required)\n  -xxxx.war（能发布到tomcat的发布包）\n  -xxxx.sql（如果需要基础测试数据导入，则提供sql脚本）\n  -readme.md（详细介绍项目发布的环境要求与步骤）","1.模板\n  1）需求规格说明书模板\n  2）测试用例模板\n  3）系统概要设计说明书模板\n  4）会议记录模板\n  5）贡献评价表\n2.文档\n  1）presentationPPT"]